## Sheet1
Story # | Card Front | Card Back | Sprint Number | Priority | Estimated Size (SML) | Estimated Size (Hours) | Actual Hours | Estimated Velocity Data | Actual Velocity Data | Changes Made After Submission 1 | Changes Made After Submission 2 | Changes Made for Deliverable 2 Submission
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality>. |  |  |  | **After this iteration, baseline may be adjusted** S = 3 Hours M= 5 Hours L = 9 Hours |  | (Estimated Size / Estimated Hours) | (Actual Hours / Estimated Hours) | **This change applies to all user stories:** Updated all user stories card front's to follow the correct format. Most of our user stories were missing the "so that <why the user wants it> portion, so it was added. Additionally, most user stories card back's were updated as well. Some were missing the properly formatted acceptance criteria. | Modified several user stories to reflect class feedback and changes in scope. Added story estimations (hours baseline may be adjusted after this iteration). | **This change applies to all user stories:** Added Sprint Number and Priority columns for all user stories (they were not added for Submission 2). Updated a few user stories due to changes in project scope, as well as class feedback. The changes described above are highlighted in yellow.
ST-1 | As a UNC Charlotte Faculty member, I should be able to access the website by logging in quickly and easily, so I can access the desired data as soon as possible. | I can successfully login and access the website in a timely manner. | Sprint 2 | 1st | S | 3 | 1 | 1 | 3
ST-2 | As a member of the UNC Charlotte Administration, I should be able to see the utilization of each building on campus so I can make sure guidlines are being followed. | I can see the average estimated occupancy and maximum occupancy of each building on campus. | Sprint 3 | 8th | S | 3 |  | 1
ST-3 | As a UNC Charlotte Faculty member, I should be able to sort buildings by traffic so I can see if the buildings are being properly utilized. | I can graphically view buildings occupancy levels. | Sprint 2 | 2nd | M | 5 | 3 | 1 | 1.6667
ST-4 | As a UNC Charlotte Faculty member, I should be able attain the current population of the campus so I can know how many individuals are currently on campus. | I can view total active population count. | Sprint 2 | 3rd | S | 3 | 3 | 1 | 1
ST-5 | As a UNC Charlotte faculty member, I would like the interface of the application to be easy to use so I can quickly find what I am looking for. | I can quickly and easily find the information I am looking for due to the application's accessibility. | Sprint 2 | 6th | M | 5 | 5 | 1 | 1
ST-6 | As a UNC Charlotte Faculty member, I should be able view changes in population during the course of the day so I can formulate better plans for emergency situations. | I can see changes in occupancy in buildings as the day progresses through visualizations, such as a line graph. | Sprint 2 | 5th | L | 9 | 3 | 1 | 3
ST-7 | As a UNC Charlotte Faculty member, I should be able to view occupancy data from previous archived days so I can compare it to the present data. | I can view data from previous days by choosing the date from a dropdown. | Sprint 2 | 4th | S | 3 | 2 | 1 | 1.5
ST-8 | As a member of GIS at UNCC, I should be able to view where people went in an emergency situation so I can modify emergency plans if needed. | I can view logged building occupancy for archived important/emegency dates. | Sprint 3 | 13th | M | 5 |  | 1
ST-9 | As Emergency Personnel, I would like to be able to view the current building occupancy so I can see if the proper fire regulation rules are being followed. | I can view the current building occupancy levels and compare them to the maximum allowed occupancy level. | Sprint 3 | 11th | S | 3 |  | 1
ST-10 | As Emergency Personnel, I would like to be sure everyone has made it out of a building during an evacuation so I know that everyone is safe. | I can filter through the data to see if any devices (people) are left in the building. | Sprint 3 | 14th | M | 5 |  | 1
ST-11 | As a UNCC student, I would like to see which places are the least populated on campus so I can find a less crowded place to study. | I can view a heatmap showing the crowdedness of specific areas around the campus. | Sprint 3 | 12th | L | 9 |  | 1
ST-12 | As a UNCC student, I would like to see how crowded each gym is before visiting so I can know if there will be enough equipment free. | I can check the occupancy of each gym to determine which one would give me the most use of equipment. | Sprint 3 | 10th | S | 3 |  | 1
ST-13 | As a UNCC faculty member, I would like to view relevant building occupancy information so I can easily find out what I need to know. | I can easily find and view all of the information related to one area or building to find out what I need to know. | Sprint 3 | 9th | M | 5 |  | 1
ST-14 | As a Moderator, I would like to alert/warn the user of the current area being crowded in real-time so I can make sure the proper saftey regulations are being followed. | I can view a real-time tracker based on the connected devices to the wifi. | Sprint 3 | 15th | L | 9 |  | 1
ST-15 | As Emergency Personnel, I would like the application and the relevant data to load quickly and efficiently so I can find out what I need to know in an emergency situation. | I can view the application and the data I requested without any noticeable delay. | Sprint 2 | 7th | L | 9 | 10 | 1 | 0.9
[5 empty] | Total for Sprint 2 | 37 | 27
[5 empty] | Velocity per Sprint | 27
[5 empty] | Velocity Per Sprint Delta (Velocity Per Sprint / Estimated Hours Total) | 0.72973
Group 10 - UNC Charlotte Analytics
User Story Cards
Description:
Aim to make sure buildings are properly utilized based on occupancy by using data about devices connected to different Wi-Fi access points. Using this, we will determine occupancy of buildings and other locations around campus.
Team Members:
Kevin Kim, Richard Scott, Manu Kakani, Chase Blackwelder, Brandon Burgess